AWS Bedrock Model Deployment and Rollout Plan: Testing Phase

Validation approach before, during and after the rollout of the Gemma 4 family on Bedrock, with the document extraction gateway on Red Hat OpenShift.

Document control

| Field | Value |
| --- | --- |
| Ticket | Jira Service Desk: Draft the testing phase of the plan for rolling out models on Bedrock, covering the validation approach to use before and after rollout. One of three phases split out of ATI1-3498, which retains the design phase. |
| Companion documents | Inputs: AWS Bedrock Model Deployment and Rollout Plan: Design Phase, version 1.1 (4 September 2026) and Deployment Phase, version 1.0 (21 September 2026). Earlier inputs: the previous Requirements and Resource and Cost Budget documents (FR and NFR identifiers are cited from the Requirements document). This document finalizes every threshold the deployment document marked as proposed. |
| Decision basis | The Gemma family on Bedrock: google.gemma-4-31b, google.gemma-4-26b-a4b and google.gemma-4-e2b, all enabled, served only on the bedrock-mantle endpoint in us-east-1, roles assigned from the bake-off. Cluster placement (ROSA or OpenShift on AWS, path A; on premises, path B) still unconfirmed; tests that differ by path say so. |
| Author | Muntaser Syed |
| Version and status | 1.0, draft for team review |
| Date | 5 October 2026 |
| Fact basis | Bedrock facts the tests depend on (model cards, bedrock-mantle quotas and metrics, the scaling and ramp guidance, the ApplyGuardrail semantics, the sensitive information filter identifiers, endpoint regional availability, the Chat Completions page) were re-read from the AWS documentation on 5 October 2026. Sample sizes and confidence intervals in this document are computed from stated assumptions with standard formulas and are planning figures, not measurements. Section 14 lists the sources. |

# 1. Purpose, scope and inputs

The design document fixed what is built and the deployment document fixed the order in which it goes live. This document fixes how the team knows it works: the tests that run before any production document touches Bedrock, the measurements that gate each production state (dark, shadow, canary, full), and the checks that continue after rollout so that a regression, a drift in the model, a cost excursion or a control failure is seen within a defined window. Every threshold the deployment document labeled as proposed is set here, with the reasoning, so that the two documents can be executed together without a further decision.

Three properties of the Gemma decision shape the test design. First, Gemma 4 is served only on bedrock-mantle, where throughput has no published quota, so throughput is proven by a ramp rather than read from a quota. Second, structured outputs and inline guardrails are not documented for Gemma 4 on that endpoint, so the schema contract and the sensitive information controls are enforced in the gateway and must be tested there, not assumed from the platform. Third, the model identifiers carry no version suffix, so behavior can change under the same identifier; the post-rollout plan therefore includes a fixed probe panel that detects drift.

## 1.1 Scope

| In scope | Out of scope |
| --- | --- |
| Pre-rollout validation: platform acceptance, provider module tests, the bake-off (FR-13) with its probes, guardrail and injection tests, throughput ramp proof, failover game day, rollback drills, security and compliance checks, cost reconciliation, operational readiness | Unit testing conventions of the gateway codebase beyond the cases named here |
| Rollout validation: shadow comparison, canary gates, ramp watch, backlog on Flex, with final thresholds | The deployment steps themselves (deployment document) |
| Post-rollout validation: production sample audit, drift canary panel, operational tracking, regression on change, periodic drills | Business acceptance of the extracted fields by the downstream teams, beyond the posting reconciliation checks named here |
| Evaluation data governance: labeling protocol, agreement measurement, versioning, privacy of test documents | The optional OCR-first arm (Section 5.6) beyond its test design; whether it is run is a bake-off scoping decision |
| Reporting: the evaluation report and the gate evidence pack | Model training or fine-tuning |

## 1.2 What this document takes from the earlier documents

| Item | Source | Used here for |
| --- | --- | --- |
| Workload: one page image plus about 800 prompt tokens in, about 1,000 JSON tokens out; 300 documents per minute peak; English, French and Spanish | Requirements, Section 2; design, Section 1.2 | Load profile, language strata, token measurements |
| NFR-01 p95 latency 20 seconds; NFR-02 300 per minute without throttling; NFR-03 backlog window; NFR-12 straight-through processing 70 percent at six months | Requirements, Section 5 | Non-functional thresholds |
| Gateway contract, retry policy, failover ladders, guardrail policy (NONE for extraction field types, ANONYMIZE for card numbers), routing table keys | Design, Sections 4.4, 6.5, 7.1, 7.3, 7.5, 8 | Provider module and guardrail test cases |
| Gemma 4 facts: bedrock-mantle only; in-region us-east-1; no batch; no published quota; 3.5 MB payload; reasoning effort; visual token budgets 70 to 1,120 on the Google card; recommended sampling temperature 1.0 and top_p 0.95 | Design, Section 6.7 | Probe design |
| Stage sequence, verification tables, canary steps, rollback ladder and triggers with proposed values | Deployment, Sections 4 to 10 | Finalized here in Sections 6 and 8 |
| Cost per document estimate per variant at Standard tier (31B about $0.00067 with the image at 1,120 tokens) | Design, Table 6.9 | Cost reconciliation tolerance |

## 1.3 Re-verification

| Item | Status on 5 October 2026 | Effect on the tests |
| --- | --- | --- |
| Gemma 4 model cards (three variants) | Unchanged: Active, no EOL date, bedrock-mantle only, in-region us-east-1, us-east-2, us-west-2 and eu-central-1; supported features listed as client-side tool calling, reasoning and Projects; 3.5 MB payload | No change; model evaluation through Bedrock's own evaluation feature is not listed for these models, so the evaluation suite is the team's |
| bedrock-mantle quotas | The quota page describes per-model, per-region input and output tokens-per-minute quotas; no Gemma 4 entry | Throughput is proven by the ramp (Section 5.7), not computed from a quota |
| Scaling and throughput best practices | Ramp procedure and the six-attempt retry budget with jitter and Retry-After unchanged; 429 is quota, 503 and 529 are capacity | Ramp protocol in Section 5.7 follows it |
| AWS/BedrockMantle metrics | Inferences, InferenceClientErrors, TotalInputTokens, TotalOutputTokens, InputTokens, OutputTokens by Project and Model; no server error, throttle or latency metric | Latency, 503 and 429 measurements come from the gateway; the platform metrics are cross-checked for counts and tokens |
| Chat Completions page | Does not document response_format, service_tier or the project header; the Projects page documents the header and the service tiers page the parameter | The response_format probe (ME-05) remains a probe, not an assumption |
| ApplyGuardrail semantics | Empty outputs when no action; masked text returned when masked; canned message when blocked; outputScope FULL returns non-detected entries for debugging | Assertions in GS-01 to GS-03 use these semantics |
| Sensitive information filter identifiers | NAME, ADDRESS, EMAIL, PHONE, US_BANK_ACCOUNT_NUMBER, US_BANK_ROUTING_NUMBER, INTERNATIONAL_BANK_ACCOUNT_NUMBER, CREDIT_DEBIT_CARD_NUMBER confirmed | Seeded documents cover each type |
| Endpoint regional availability | bedrock-mantle in us-east-1, us-east-2, us-west-2 and sa-east-1 in the Americas; not in ca-central-1 or ca-west-1 | SC-02 asserts every CreateInference event is in us-east-1 |

# 2. Validation overview

Figure 1 places the test groups against the rollout. Before rollout, the groups run in dev and test and produce the evidence that the deployment document's test exit gate requires. During rollout, the shadow comparison and the canary gates decide each traffic step. After rollout, four continuing checks keep the evidence current. Table 2.1 lists the groups with their identifiers, which the test cases in Sections 4 to 9 use.

Figure 1. Validation before, during and after the rollout

Table 2.1. Test groups

| Group | Identifier | When | Environment | Gate it feeds |
| --- | --- | --- | --- | --- |
| Platform acceptance | PT | After deployment Stages 1 and 2 in each environment | dev, test, prod | Stage 1 and 2 exit |
| Provider module | PM | Build pipeline and dev | pipeline, dev | Dev exit |
| Model evaluation (bake-off) | ME | Stage 4 | test | Test exit; role assignment |
| Guardrail and safety | GS | Stage 3 and 4 | dev, test | Dev and test exit |
| Non-functional | NF | Stage 4 | test | Test exit |
| Security and compliance | SC | Stages 1, 2 and 4; repeated in prod before canary | all | Stage exits; pre-flight |
| Cost | CO | Stage 4; repeated in canary | test, prod | Test exit; canary |
| Operational readiness | OR | Stage 4 and pre-flight | test, prod | Pre-flight |
| Rollout validation | RV | Stage 5 | prod | Each canary step |
| Post-rollout | PO | Stage 6 and steady state | prod | Continuing |

## 2.1 Principles

- Every test has an identifier, a precondition, a procedure, a measurable expected result and an owner; a test without a number in its expected result is not finished.

- Thresholds are set in this document and changed only by a reviewed revision; the deployment document's proposals are superseded by Section 6.

- Accuracy claims are paired comparisons on the same documents (the previous model and each Gemma 4 variant see identical inputs), reported with confidence intervals; a single point estimate is not an acceptance.

- No production document enters dev. Test uses approved documents under the data handling rules in Section 3; production validation uses live documents only in shadow and canary, under the posting rules of the deployment document.

- Platform metrics are cross-checked against gateway metrics for every load test, because the AWS/BedrockMantle namespace publishes counts and tokens but not latency or capacity errors.

- A failed gate is reported with the measured value, the threshold, and the deployment rollback level that applies; it is never softened by re-running until it passes.

# 3. Test environments, data and tooling

Table 3.1. Environments

| Environment | Data allowed | Bedrock traffic | Used by |
| --- | --- | --- | --- |
| Pipeline (Tekton) | Recorded responses, synthetic images | None (contract tests replay recorded responses) | PM |
| dev | Synthetic documents only (generated invoices and receipts with known field values, seeded PII and injection text) | Live, small volume, dev Project | PT, PM, GS, OR |
| test | Approved document set: the labeled evaluation set and the load corpus, both cleared by information security for use outside production; no live customer documents | Live, up to the ramp ceiling, test Project | PT, ME, GS, NF, SC, CO, OR |
| prod | Live documents, only in shadow and canary under deployment Stage 5 | Live, prod Project | PT, SC, RV, PO |

## 3.1 Evaluation data

The labeled evaluation set is the asset the bake-off, the shadow comparison and the post-rollout audit all depend on. Its size follows from the comparisons it must support. For a paired comparison of field accuracy between the previous model and a Gemma 4 variant, the planning assumption is a baseline field accuracy of 95 percent and a minimum difference worth detecting of 2 percentage points; with a two-sided 5 percent significance level and 80 percent power, the normal approximation for two proportions gives about 2,213 field instances per arm. The paired design needs fewer, so this is a conservative planning figure. Fields within a document are correlated, so the figure is met by documents rather than by counting fields: with about 15 fields per document, 500 documents per language stratum give 7,500 field instances per stratum and leave room for per-field analysis of the sparse fields.

| Property | Specification | Reason |
| --- | --- | --- |
| Size | At least 500 labeled documents per language (English, French, Spanish), stratified by document type (invoice, receipt) and by vendor template coverage, with at least 50 documents per major vendor template and a long tail of unseen vendors | Sample size planning above; per-template analysis for the cache layers |
| Labels | Every schema field, including nulls for absent fields; amounts as decimals; dates in ISO 8601; a document-level flag for quality issues (skew, low contrast, handwriting) | Null handling and hard-case analysis |
| Labeling protocol | Two independent annotators per document; disagreements adjudicated by a third; inter-annotator agreement reported per field as Cohen's kappa and required to be at least 0.8 before the set is frozen | Label noise bounds the measurable accuracy |
| Previous model baseline | The previous model's outputs on the same set, produced before the bake-off and frozen | Paired comparison |
| Versioning | Set index, labels and baseline outputs in Git with a content hash; documents in the evaluation bucket under the environment KMS key; every report cites the set hash | Reproducibility |
| Probe panel | A fixed subset of 50 documents (balanced across languages and types) with reference outputs per variant, frozen at role assignment | Drift canary (PO-2) |
| Seeded sets | Guardrail set: at least 200 synthetic documents with full card numbers, bank account and routing numbers, IBANs, names, addresses, emails and phones placed in realistic positions; injection set: at least 100 pairs of the same document with and without embedded instruction text | GS tests |
| Load corpus | At least 5,000 approved pages covering the size distribution of production scans, used only for throughput and latency | NF tests |

## 3.2 Tooling

| Tool | Purpose | Notes |
| --- | --- | --- |
| Evaluation suite (team repository) | Runs a model configuration against the set, scores fields, computes calibration, latency and token statistics, writes the evaluation report | Bedrock's built-in evaluation feature is not listed for Gemma 4 on bedrock-mantle, so the suite calls the gateway's provider module directly with a fixed routing table |
| Load generator | Replays the load corpus at a controlled rate through intake, with ramp steps and holds | Runs from a separate project on the cluster; records per-request outcome |
| Fault injection | Forces breaker states, injects 429, 503 and 529 responses, drops credentials, kills pods | Provider module test hooks enabled only in dev and test |
| Comparison job | Pairs Bedrock path outputs with previous path outputs by document and page; computes agreement and routes disagreements to review | Used in shadow (RV-1) and the audit (PO-1) |
| Report template | Evaluation report sections: set hash, configurations, per-language and per-field accuracy with intervals, calibration, latency, tokens, cost, probe results, recommendation | Attached to the role assignment pull request |

# 4. Pre-rollout validation: platform and provider module

## 4.1 Platform acceptance (PT)

| ID | Test | Procedure | Expected result |
| --- | --- | --- | --- |
| PT-01 | Private path | From a gateway pod resolve bedrock-mantle.us-east-1.api.aws, bedrock-runtime.us-east-1.amazonaws.com and sts.us-east-1.amazonaws.com; make one call each; read the VPC flow logs for the endpoint network interfaces | All three resolve to private addresses (cluster VPC on path A; landing VPC on path B); flow logs show the calls; no traffic to public Bedrock addresses |
| PT-02 | Credential path | sts get-caller-identity from the gateway pod; path A with the annotated service account, path B through the credential helper; wait past one credential rotation and repeat | docext-gateway-role for the environment, before and after rotation |
| PT-03 | Least privilege | Policy simulator and live calls: CreateInference on another project ARN; ApplyGuardrail on another guardrail; InvokeModel on any model; CreateProject | All denied; CreateInference on the environment project allowed |
| PT-04 | Project and retention | GetProject; GET the project retention mode; GET /v1/models/{model} for each variant | ACTIVE with the four tags; mode none; allowed_modes include none for each variant |
| PT-05 | Models listed | GET /v1/models on bedrock-mantle | The three Gemma 4 identifiers present |
| PT-06 | First invocation and subscription | One Chat Completions call per variant with a synthetic page | JSON returned; usage populated; if AccessDeniedException occurs within the first 15 minutes, re-test after the subscription window before diagnosing permissions |
| PT-07 | Observability | After PT-06, read AWS/BedrockMantle Inferences and token metrics by Project and Model; read the CloudTrail CreateInference data event; read the gateway metadata line | Counts match the calls; event shows the project and model; metadata line present with the request ID |
| PT-08 | Cost attribution (24 hours later) | Cost Explorer by project tags and by IAM principal tags | Spend from PT-06 visible against the environment project |
| PT-09 | Guardrail round trip | ApplyGuardrail with the pinned version on a text containing a card number and on a text containing an address | Card number returned masked; address detected with outputs empty (no action) |
| PT-10 | Alarms | Publish synthetic metric values for each alarm | Each alarm transitions to ALARM and notifies the on-call channel |

## 4.2 Provider module (PM)

| ID | Test | Procedure | Expected result |
| --- | --- | --- | --- |
| PM-01 | Request shape | Capture the request for a synthetic page | Base URL on the /openai/v1 path; model identifier from the routing table; system prompt first; image_url data URL before the text; max_tokens 1,500; temperature and top_p from the table; reasoning effort from the table; service_tier default; OpenAI-Project header equal to the environment project; metadata field contains no identifiers or document content |
| PM-02 | Authentication | Run with auth.mode sigv4 and with short_term_token; force token expiry | Both modes succeed; the token mode refreshes before expiry; no long-term key is ever generated (SCP would deny it) |
| PM-03 | Retry budget | Inject 429 with and without Retry-After, 503, 529 | At most six attempts; backoff grows with jitter; Retry-After honored; no retry on 400 or AccessDeniedException |
| PM-04 | Rate limiter in ramp mode | Configure a baseline and step; inject sustained 503 on the third level | Ceiling rises only after a clean hold; halves on sustained 503; admission counts input tokens plus max_tokens |
| PM-05 | Breaker and failover | Inject 503 above the breaker rate for the primary | Breaker opens within the window; requests route to the secondary; the tripping request completes on the secondary; half-open probe restores |
| PM-06 | Schema validation | Replay responses: valid, missing required field, wrong type, out-of-range confidence, extra field, totals inconsistent with line items | Each invalid case fails validation with the named rule; one corrective retry; then escalation |
| PM-07 | Truncation and malformed output | Replay finish_reason length and malformed JSON | Truncation triggers one retry with max_tokens raised by 50 percent and records the event; malformed JSON triggers the corrective retry |
| PM-08 | Guardrail post-processing | Replay an output with a card number | ApplyGuardrail called with the pinned version; anonymized text stored; document flagged for review; Luhn check records a second detection |
| PM-09 | Payload limit | Submit a page encoded above 3.5 MB | Rejected before the call with a sizing error; a page at the upstream resize cap passes |
| PM-10 | Idempotency | Kill the gateway pod mid-request; replay the message | One posting per document and page; the metadata line shows the retry |
| PM-11 | Traffic share and shadow | Set traffic_share 0.1 and shadow_mode true; run 1,000 synthetic documents | Between 8 and 12 percent (hash-based) take the Bedrock path; nothing from the Bedrock path is posted; comparison records written |
| PM-12 | Readiness probe | Deny ListModels for the role temporarily | Pod reports not ready; traffic shifts to healthy pods; restored when the permission returns |

# 5. Pre-rollout validation: model evaluation, safety, non-functional, controls, cost and readiness

## 5.1 Metrics and scoring rules

| Metric | Definition | Reported as |
| --- | --- | --- |
| Field accuracy | A field is correct when its normalized value equals the label: amounts equal to the cent; dates equal after ISO 8601 normalization; strings equal after case, whitespace and diacritic normalization; identifiers exact; a null is correct only when the label is null | Per field, per language, per variant, with a 95 percent interval; paired difference against the previous model with a McNemar test on the per-field correct and incorrect pairs |
| Document accuracy | All required fields correct | Share of documents, with interval |
| Schema validity | Response parses and passes the validator without the corrective retry | Share of responses; rate after the retry reported separately |
| Null precision and recall | For optional fields: precision of non-null extractions and recall of labeled values | Per field |
| Calibration | Reliability diagram of calibrated confidence against observed field correctness; expected calibration error (ECE) with 10 equal-width bins; Brier score | Per variant; ECE threshold in Section 6 |
| Straight-through rate (projected) | Share of documents whose required fields all exceed the review threshold and are correct | Per variant; the thresholds that reach the NFR-12 target with the required precision are derived here |
| Latency | End to end from gateway receipt to validated result; model time from the provider call | p50, p95, p99 per variant at the baseline rate and at the target rate |
| Tokens | usage.prompt_tokens and usage.completion_tokens; image tokens by difference against a text-only request; reasoning tokens by difference across effort settings | Mean and p95 per document, per variant |
| Cost per document | Tokens multiplied by the list prices on the day of the run, per tier | Mean per variant; compared with the design estimate |

## 5.2 Model evaluation and probes (ME)

| ID | Test | Procedure | Expected result and use |
| --- | --- | --- | --- |
| ME-01 | Bake-off run | Each variant on the full labeled set through the provider module with the routing table fixed at the bake-off configuration (temperature 0, reasoning at the lowest setting, max_tokens 1,500); the previous model baseline loaded from Git | Evaluation report with every metric in Section 5.1; the variant ordering by field accuracy with intervals |
| ME-02 | Per-language and hard cases | Break down by language and by the quality flag | No language below the threshold in Section 6; hard-case accuracy reported for the review threshold design |
| ME-03 | Calibration fit | Fit the calibration layer per variant on a held-out half of the set; evaluate on the other half | ECE and Brier per variant; curve versions recorded for the routing table |
| ME-04 | Threshold derivation | Sweep the review threshold on calibrated confidence; compute precision of auto-posted fields and the projected straight-through rate | The threshold pair (escalate, review) that gives at least 99 percent precision on auto-posted required fields, with the resulting straight-through rate reported against the NFR-12 trajectory |
| ME-05 | response_format probe | Send the extraction request with the OpenAI response_format json_schema object on Chat Completions and with text.format on Responses, for each variant | Record whether the endpoint accepts the field, rejects it, or ignores it, and whether conformance improves; the gateway validator remains the contract whatever the result |
| ME-06 | Determinism probe | Repeat 50 documents 10 times each per variant at temperature 0 | Field-level agreement across repeats at least 99 percent; the mixture-of-experts variant reported separately; below the threshold, the regression suite uses majority agreement over three runs |
| ME-07 | Reasoning probe | Run 200 documents per variant at each reasoning setting the endpoint accepts (lowest, medium, high, and disabled where the API allows it) | Completion tokens, accuracy and any reasoning text in the content per setting; the lowest setting whose accuracy is within 0.5 points of the best is pinned; leakage into the content must be zero |
| ME-08 | Image token measurement | For 200 pages, send the request with and without the image at the production resize cap and at two smaller long-edge sizes | Image tokens per page per size; accuracy per size; the resize policy that keeps accuracy within 0.5 points of the largest at the lowest token count is adopted; the design estimate of 1,120 tokens is replaced by the measurement |
| ME-09 | Sampling probe | Compare temperature 0 against the AWS general recommendation (temperature 1.0, top_p 0.95) on 200 documents | Accuracy and determinism per setting; temperature 0 retained unless it loses more than 0.5 points |
| ME-10 | Implicit caching observation | Inspect usage for cached token fields over a run with the static prefix first | Report whether cached input tokens are reported and their share; no threshold |
| ME-11 | Prompt and schema regression | Re-run ME-01 after any prompt or schema change on the frozen set | No field loses more than 0.5 points without a reviewed justification |

## 5.3 Guardrail and safety (GS)

| ID | Test | Procedure | Expected result |
| --- | --- | --- | --- |
| GS-01 | Card number control | Guardrail set through the full path | Every full card number in model output is anonymized by ApplyGuardrail before storage; the Luhn check agrees; every such document reaches the review queue; zero card numbers in the extracted topic, the metadata line or the logs |
| GS-02 | Extraction fields preserved | Guardrail set | Names, addresses, emails, phones, bank account and routing numbers and IBANs are returned unchanged with a detection recorded (outputs empty from ApplyGuardrail, detection in the assessment) |
| GS-03 | Content filter false positives | Full labeled set | Share of legitimate outputs blocked by the content filters below 0.5 percent; each block reviewed and the filter strength adjusted only by a reviewed change |
| GS-04 | Prompt injection | Injection pairs (same document with and without embedded instruction text) | Schema violations after validation: zero (the validator guarantees it); field values changed by the injected text in at most 1 percent of pairs; no extra fields; no instruction text reproduced in any field |
| GS-05 | Abuse detection on images | Submit the abuse detection probe images AWS documents as blocked, where available, otherwise a synthetic unsafe image | Request rejected with the documented error; routed to review with a security notification; no retry |
| GS-06 | Guardrail version pinning | Publish a new guardrail version in test without changing the routing table | The gateway keeps calling the pinned version; a routing table change is required to adopt the new one |

## 5.4 Non-functional (NF)

| ID | Test | Procedure | Expected result |
| --- | --- | --- | --- |
| NF-01 | Latency at baseline | Load corpus at the Stage 2 baseline rate for 15 minutes per variant | p95 within NFR-01 (20 seconds); p50 and p99 recorded; path B adds the measured Direct Connect round trip, which must still fit |
| NF-02 | Throughput ramp proof | Section 5.7 protocol on the primary variant to 300 per minute, then toward headroom | Sustained 300 per minute for the hold period with capacity errors below the threshold; ceiling recorded; headroom reported |
| NF-03 | Secondary under failover load | Ramp the secondary to the share it must carry when the primary is open (the full 300 per minute if the design keeps one secondary) | Same criteria as NF-02 at that rate |
| NF-04 | Failover game day | Fault injection: primary breaker open; then primary and secondary open; then restore | First successful response on the secondary within the breaker window (60 seconds); dead letter routing and the alarm within 2 minutes when both are open; restoration without manual action |
| NF-05 | Rollback drill | Execute L1 by pull request and by break-glass, L2, and L3 in test, timed | L1 by pull request within 15 minutes; L1 by break-glass within 5 minutes; L2 within 15 minutes; L3 within 15 minutes; verification of each as in the deployment ladder |
| NF-06 | Backlog on Flex | Drain a test backlog of 10,000 pages with service_tier flex at the configured rate | Completion within the NFR-03 window; capacity errors below threshold; Flex requests confirmed by the gateway record |
| NF-07 | Credential and certificate rotation under load | Run NF-01 across an STS rotation (path A) or a certificate renewal (path B) | No failed requests attributable to rotation |
| NF-08 | Pod disruption | Drain a node during NF-01 | No lost or duplicated documents; p95 within threshold after rebalancing |

## 5.5 Security and compliance (SC), cost (CO) and operational readiness (OR)

| ID | Test | Procedure | Expected result |
| --- | --- | --- | --- |
| SC-01 | Organization controls | Attempt Bedrock calls in eu-central-1; attempt a long-term key; attempt a retention mode change from a non-platform role; attempt CreateProject from the gateway role | All denied by the SCP or IAM; denials visible in CloudTrail |
| SC-02 | Residency evidence | Query CloudTrail for every CreateInference event over a test run | Every event in us-east-1 under the environment project; none elsewhere |
| SC-03 | Audit join | Pick 50 documents; join the metadata line, the CloudTrail event and the posting record by request ID and document ID | All 50 join; no content in the audit records |
| SC-04 | Metadata hygiene | Inspect CloudTrail CreateInference events | The metadata field carries only the agreed keys, no identifiers or document content |
| SC-05 | SIEM rules | Fire each rule with a synthetic event (foreign principal, model outside the allow list, retention change, project archive) | Each rule alerts within the SIEM's delivery window |
| SC-06 | Retention position | PT-04 repeated in prod before the canary; plus GET /v1/models for each variant | Account none; project none; allowed_modes include none |
| CO-01 | Cost reconciliation | After ME-01 and NF-02, compare tokens times list price with Cost Explorer by project and by principal after 24 hours | Agreement within 5 percent; the difference explained (tier mix, CloudTrail data events, guardrail units) |
| CO-02 | Cost per document against the estimate | Mean cost per document per variant from ME-01 with measured image and reasoning tokens | Within 20 percent of the design estimate at Standard; otherwise the estimate is revised and the budget document amended before production |
| CO-03 | Budget alarms | Set a temporary budget below the test spend | Alarms at 80 and 100 percent fire |
| OR-01 | Runbook walkthrough | Operations executes the capacity, rollback and credential runbooks on test | Each runbook completes without an undocumented step |
| OR-02 | Dashboards | Review during NF-02 | Gateway and platform panels show the ramp, errors, tokens and cost; no panel depends on a metric the namespace does not publish |
| OR-03 | Break-glass | Assume the break-glass role; perform an L1 edit; revert | Assumption alerted in the SIEM; edit reconciled by the pull request |

## 5.6 Optional OCR-first arm

If the platform team pursues the deployment document's option C, the bake-off gains one arm: PaddleOCR-VL-1.6 served on OpenShift AI or a SageMaker endpoint parses each page to Markdown, and a text-only request to the same Gemma 4 variant maps the text to the schema. The arm runs ME-01, ME-02, ME-06 and the cost metric with the two-step latency included, against the image-to-JSON arm on the same set. It is adopted for a document class only where it wins on accuracy at equal or lower cost per document, and it is never a failover on its own because it still depends on the extractor.

## 5.7 Throughput ramp protocol

The ramp follows the AWS procedure for the bedrock-mantle endpoint, where Gemma 4 has no published quota and capacity is governed by the service. The protocol below fixes the parameters the deployment document left as proposals.

| Parameter | Value | Reason |
| --- | --- | --- |
| Control signals | Input tokens plus max_tokens per minute, completion tokens per minute, and concurrency; requests per minute recorded but not used as the control | The endpoint has no RPM quota and AWS advises against RPM as the only signal |
| Starting level | The Stage 2 stable baseline (10 documents per minute for 15 minutes with zero capacity errors) | A known stable baseline below the target |
| Step | Raise the admitted rate by 50 percent per step | Matches the AWS launch guidance and keeps steps countable |
| Hold | 15 minutes per level, or longer if the p95 window needs it | Enough to observe 429, 503, 529, latency percentiles, tokens and concurrency per level |
| Regression | Capacity errors (503 plus 529) above 2 percent of requests over the hold, or 429 sustained after backoff, or p95 above 20 seconds | Pause, honor Retry-After, return to the last stable level, re-hold |
| Target | 300 documents per minute, then continue toward 600 per minute (2 times peak) while the regression rule is not triggered | AWS suggests planning headroom of two to three times the expected peak; the ceiling found is the production ramp ceiling |
| Repeat | Per variant that will carry production traffic (primary and secondary), and again in production behind the canary | Capacity differs by model and over time |
| Record | Per level: rate, concurrency, input and output tokens per minute, error counts by code, p50 and p95, CloudWatch token totals for the cross-check | Evidence for the quota support case |

# 6. Acceptance thresholds (finalized)

Table 6.1 replaces the proposed values in the deployment document. Where a threshold is a non-inferiority margin, the comparison is paired on the same documents and the interval must exclude the margin.

| Gate | Criterion | Threshold | Basis |
| --- | --- | --- | --- |
| Dev exit | Contract and smoke tests | All pass | PM, PT in dev |
| Dev exit | Schema validity after the corrective retry (synthetic set) | Failure below 2 percent | Design document NFR-12 margin |
| Test exit | Field accuracy of the primary variant, per language, paired against the previous model | Non-inferior at a 1 point margin: the lower bound of the 95 percent interval on the difference is above minus 1 point; no field with more than a 3 point drop | Business tolerance for a model change; the sample size supports a 2 point detection |
| Test exit | Document accuracy | Not below the previous model by more than 2 points | Same |
| Test exit | Schema validity after retry | Failure below 2 percent on the labeled set | As dev |
| Test exit | Calibration | ECE at or below 0.05 per variant on the held-out half | Review routing depends on calibrated confidence |
| Test exit | Auto-post precision at the derived threshold | At least 99 percent on required fields | Posting into the ledger systems |
| Test exit | Determinism at temperature 0 | Field agreement at least 99 percent across repeats | Regression testing needs repeatable outputs |
| Test exit | Reasoning leakage | Zero reasoning text in any field | Schema contract |
| Test exit | Latency | p95 at or below 20 seconds at 300 per minute | NFR-01 |
| Test exit | Throughput | 300 per minute sustained for a 15 minute hold with capacity errors below 2 percent | NFR-02; ramp protocol |
| Test exit | Failover | Secondary serving within 60 seconds of breaker open | Design breaker window |
| Test exit | Rollback | L1 within 15 minutes by pull request and 5 minutes by break-glass; L2 and L3 within 15 minutes | Operational target |
| Test exit | Guardrail | Card numbers anonymized 100 percent; extraction fields preserved 100 percent; content filter false positives below 0.5 percent | GS |
| Test exit | Injection | Field changes in at most 1 percent of injected pairs; zero schema violations | GS-04 |
| Test exit | Cost | Within 20 percent of the design estimate at Standard; reconciliation within 5 percent of Cost Explorer | CO |
| Shadow | Agreement with the previous path | Sample of at least 1,825 documents; disagreements reviewed; Bedrock path correct in at least as many reviewed disagreements as the previous path | Section 7.1 |
| Canary | See Table 7.2 | See Table 7.2 | Section 7.2 |

# 7. Rollout validation (during the canary)

## 7.1 Shadow comparison (RV-1)

The shadow state runs the Bedrock path on a sample of live documents without posting its results. Its purpose is to estimate the disagreement rate between the two paths on real traffic and to review the disagreements. To estimate a disagreement rate assumed near 5 percent within plus or minus 1 percentage point at 95 percent confidence requires about 1,825 documents, so the shadow sample is at least 2,000 documents and at least 200 in each document class and language. Each disagreement is reviewed by a person who records which path was right; the Bedrock path must be right at least as often as the previous path, and any field with a systematic error pattern blocks the first canary step until the prompt or threshold is adjusted and the shadow repeated.

| Measure | Procedure | Threshold |
| --- | --- | --- |
| Sample | traffic_share set to the shadow share (10 percent) with shadow_mode true until the sample is complete across strata | At least 2,000 documents; at least 200 per class and language |
| Agreement | Field-level agreement between the paths on the comparison job | Reported with interval; disagreements reviewed |
| Who was right | Human review of every disagreement | Bedrock path correct in at least 50 percent of disagreements overall and no required field below 40 percent |
| Schema validity | As in test | Below 2 percent after retry |
| Capacity | 503 and 529 share during shadow | Below 2 percent |
| Cost | Mean cost per document on the shadow sample | Within 20 percent of the design estimate |

## 7.2 Canary gates (RV-2)

Table 7.2. Canary steps, holds and criteria (finalized)

| Step | Share | Hold | Criteria to proceed | Rollback trigger |
| --- | --- | --- | --- | --- |
| 1 | 5 percent | One business day and at least 1,000 documents on the Bedrock path | Posting reconciliation clean for every Bedrock-path document; schema failure below 2 percent; review queue rate for Bedrock-path documents not above the previous path's rate plus 10 percent relative; p95 within 20 seconds; capacity errors below 2 percent; no SIEM event | Any reconciliation break; capacity errors above 5 percent for 10 minutes after one halving; p95 above 20 seconds for 10 minutes; any SIEM event |
| 2 | 25 percent | Two business days | Step 1 criteria plus the production sample audit (PO-1 procedure on 100 Bedrock-path documents) non-inferior to the previous path at the 1 point margin; AWS ramp holding at the matching rate | As step 1 |
| 3 | 50 percent | Two business days | Step 2 criteria plus cost per document within 20 percent of the estimate over the hold | As step 1 |
| 4 | 100 percent | Stabilization: ten business days before the previous path is retired | Step 3 criteria plus the projected straight-through rate tracking the NFR-12 trajectory; the quota support case updated with production ramp data | As step 1; retirement deferred on any open finding |

## 7.3 Ramp and rollback watch (RV-3) and backlog on Flex (RV-4)

| ID | Check | Procedure | Threshold |
| --- | --- | --- | --- |
| RV-3a | Production ramp | Section 5.7 protocol behind each canary step, starting from the test ceiling scaled to the share | Regression rule as in Section 5.7 |
| RV-3b | Rollback triggers | The triggers in Table 7.2 and the deployment document's Table 10.2 with the values from Section 6 | Trigger leads to the stated level; executor and time recorded |
| RV-3c | Drill confirmation | L1 by pull request executed once in production during step 1 as a planned exercise (share reduced then restored) | Within 15 minutes; documents in flight handled as in the deployment document Section 10.3 |
| RV-4 | Backlog on Flex | After step 4, drain the production backlog at the proven rate | Completion within the NFR-03 window; capacity errors below 2 percent |

# 8. Post-rollout validation

## 8.1 Production sample audit (PO-1)

A weekly random sample of Bedrock-path documents, stratified by language and document type, is reviewed by people against the posted values, and the result is reported as field and document accuracy with intervals. The sample size sets the precision: 100 documents give a document-accuracy interval of about plus or minus 6 points at an assumed 90 percent, which is enough to catch a large regression within a week; the monthly roll-up of 400 documents narrows it to about plus or minus 3 points, which is the figure compared with the test exit result. A monthly result more than 2 points below the test exit result opens an investigation; more than 5 points triggers the regression suite and, if confirmed, the role swap or the previous path by the deployment ladder while it is still deployed.

## 8.2 Drift canary panel (PO-2)

The model identifiers carry no version, so the panel of 50 frozen documents with reference outputs per variant runs daily against each variant through the production provider module (shadow mode, nothing posted). Field agreement with the references is the signal: below 98 percent for two consecutive days, or any change in usage patterns (prompt or completion tokens per document shifting by more than 10 percent), raises an engineering alarm and triggers the regression suite on the labeled set. The panel also detects endpoint-side changes such as a different reasoning default or a changed image tokenization.

## 8.3 Operational tracking (PO-3)

| Signal | Cadence | Threshold or target | Action |
| --- | --- | --- | --- |
| Straight-through processing rate | Weekly, monthly trend | Trajectory toward 70 percent at six months (NFR-12) | Threshold review (ME-04 re-run) if the trajectory falls behind for two months |
| Review queue volume and reasons | Weekly | Not above the previous path's rate plus 10 percent relative; card number flags and guardrail blocks itemized | Prompt, threshold or guardrail review |
| Calibration | Monthly on the audit sample | ECE at or below 0.05 | Re-fit the curve on recent audited documents |
| Schema failure rate | Daily | Below 2 percent after retry | Engineering ticket |
| Capacity errors and latency | Daily | Capacity errors below 2 percent; p95 within 20 seconds | Ramp ceiling review; Priority tier consideration; quota case update |
| Tokens per document | Weekly | Within 10 percent of the bake-off measurement | Drift investigation |
| Cost per document and spend | Weekly during the first quarter, then monthly | Within 20 percent of estimate; budget alarms quiet | Finance review |
| Alarm verification | Monthly | Every alarm exercised with a synthetic value | Fix silent alarms |
| Lifecycle | Quarterly | Model cards checked for Legacy state and EOL dates | Plan the swap through the regression suite |
| Controls | Quarterly | SC-01 to SC-06 repeated | Remediate |

## 8.4 Regression on change and periodic drills (PO-4)

| Change or event | Required validation | Gate |
| --- | --- | --- |
| Prompt or schema change | ME-11 on the frozen set; GS-04 injection set; PM-06 | No field loses more than 0.5 points; thresholds re-derived if the schema changes |
| Model role change or new Gemma release | Full bake-off (ME-01 to ME-10) on the frozen set; NF-02 ramp; shadow at 10 percent for at least 2,000 documents | Section 6 test exit criteria |
| Guardrail version change | GS-01 to GS-03 and GS-06 | 100 percent on the control cases |
| Gateway release | PM suite; dev and test smoke; canary at 5 percent for one business day | Dev and test exit criteria |
| Routing table change (thresholds, ramp settings) | ME-04 re-run where thresholds change; NF-02 where ramp settings change | Section 6 |
| Quarterly | NF-04 game day and NF-05 rollback drill in test; RV-3c exercise in production | Timings within Section 6 |

# 9. Reporting and evidence

| Artifact | Content | Produced at | Consumer |
| --- | --- | --- | --- |
| Evaluation report | Set hash; configurations; per-language and per-field accuracy with intervals and the paired test; calibration; thresholds derived; latency; tokens; cost; probe results (ME-05 to ME-10); recommendation | ME-01 to ME-10 | Role assignment pull request; change board; model risk review (NFR-10) |
| Ramp record | Per-level table from Section 5.7; ceiling; headroom; CloudWatch cross-check | NF-02, NF-03, RV-3a | Quota support case; test exit |
| Game day and drill record | Timings and observations | NF-04, NF-05, RV-3c | Test exit; operations |
| Controls evidence | SC results with CloudTrail extracts | SC | Information security; audit |
| Shadow report | Agreement, disagreement review, cost | RV-1 | Canary step 1 approval |
| Canary gate record | Per step: measured values against Table 7.2 | RV-2 | Change board |
| Audit report | Weekly and monthly accuracy with intervals; drift panel results | PO-1, PO-2 | Operations; model risk review |

# 10. Validation risks

| Risk | Effect | Mitigation |
| --- | --- | --- |
| Label noise in the evaluation set hides a real difference | A non-inferiority result that is wrong in either direction | Agreement requirement (kappa at least 0.8) before freeze; adjudication; noise bound reported alongside the accuracy |
| Evaluation set not representative of production traffic | Test exit passes, shadow fails | Stratification by language, type and vendor; shadow on live traffic before any posting |
| Capacity differs between test and production time windows | Ramp passes in test, 503 responses in production | Ramp repeated behind the canary; rollback trigger on capacity errors |
| Model behavior changes under the same identifier | Silent accuracy or cost change | Daily drift panel; token monitoring; regression suite on alarm |
| Reasoning setting not controllable as expected | Cost or leakage | ME-07 measures every setting the API accepts; leakage threshold zero |
| Shadow comparison biased by the previous path's own errors | Disagreement review mislabels the Bedrock path | Reviewers judge against the document, not against either path |
| Audit sample too small to see a moderate regression quickly | Weekly precision about plus or minus 6 points | Monthly roll-up; the drift panel catches systematic changes faster than the audit |

# 11. Traceability

| Requirement | Tests |
| --- | --- |
| FR-01 image input | PM-01, PM-09, ME-08 |
| FR-02 JSON contract | PM-06, PM-07, ME-05, GS-04 |
| FR-03 confidence | ME-03, ME-04, PO-3 calibration |
| FR-04 and FR-05 gateway and configuration | PM-01, PM-11, PT-03 |
| FR-07 service tier per request | NF-06, RV-4 |
| FR-08 pinned identities | GS-06, PO-2 |
| FR-10 guardrails | PT-09, PM-08, GS-01 to GS-03 |
| FR-11 logging | PT-07, SC-03, SC-04 |
| FR-12 retries, idempotency, failover | PM-03, PM-05, PM-10, NF-04 |
| FR-13 evaluation suite | ME-01 to ME-11 |
| FR-14 languages | ME-02; strata in Section 3.1 |
| FR-15 cost attribution | PT-08, CO-01 |
| NFR-01 latency | NF-01, NF-02, Table 7.2 |
| NFR-02 throughput | NF-02, NF-03, Section 5.7 |
| NFR-03 backlog window | NF-06, RV-4 |
| NFR-05 resilience | NF-04, NF-07, NF-08 |
| NFR-07 security | PT-01, PT-02, PT-03, SC-01, SC-04 |
| NFR-08 residency | SC-02 |
| NFR-09 retention | PT-04, SC-06 |
| NFR-10 compliance evidence | Section 9 |
| NFR-11 observability | PT-07, PT-10, OR-02 |
| NFR-12 quality | ME-04, PO-1, PO-3 |
| NFR-13 cost governance | CO-01 to CO-03, PO-3 |
| NFR-14 lifecycle | PO-3 lifecycle, PO-4 |
| NFR-15 maintainability | PO-4 |

# 12. Closing the ticket series

With this document the three phases of the rollout plan are complete: the design document fixes the architecture and the decisions, the deployment document fixes the sequence and the rollback, and this document fixes the evidence. Two inputs remain open across all three and are repeated here because they are the first gates in the deployment sequence: the data residency ruling that accepts in-region processing in us-east-1, and the EULA review of the Gemma 4 terms. The cluster placement decision selects path A or B in the platform tests but changes no threshold. The independent failover (deployment document Section 11) is a separate change with its own validation under Section 8.4 when it is chosen.

# 13. Sources and verification

AWS documentation pages were read on 5 October 2026 in their markdown form from docs.aws.amazon.com. Facts carried from the design and deployment documents keep their 4 and 21 September 2026 verification dates. Statistical formulas used for planning are the standard normal approximations for proportions; the inputs and outputs are stated in the text so the figures can be recomputed.

| Source | Used for | URL |
| --- | --- | --- |
| Model cards: Gemma 4 31B, 26B-A4B, E2B | Lifecycle, endpoint, regions, features, payload limit | https://docs.aws.amazon.com/bedrock/latest/userguide/model-card-google-gemma-4-31b.html |
| Quotas for the bedrock-mantle endpoint | Quota structure; no Gemma 4 entry | https://docs.aws.amazon.com/bedrock/latest/userguide/quotas-mantle.html |
| Scaling and throughput best practices | Ramp procedure, error semantics, retry budget | https://docs.aws.amazon.com/bedrock/latest/userguide/scaling-throughput-best-practices.html |
| Monitor bedrock-mantle: CloudWatch metrics | Metric names and dimensions | https://docs.aws.amazon.com/bedrock/latest/userguide/monitoring-mantle-metrics.html |
| Use the ApplyGuardrail API | Output semantics, outputScope | https://docs.aws.amazon.com/bedrock/latest/userguide/guardrails-use-independent-api.html |
| Guardrails: sensitive information filters | PII type identifiers | https://docs.aws.amazon.com/bedrock/latest/userguide/guardrails-sensitive-filters.html |
| Chat Completions API | Endpoint and authentication statements; absence of response_format documentation | https://docs.aws.amazon.com/bedrock/latest/userguide/inference-chat-completions.html |
| Regional availability by endpoints | bedrock-mantle regions | https://docs.aws.amazon.com/bedrock/latest/userguide/endpoints-region-availability.html |
| Supported Regions and models for model evaluation | Evaluation support is per model card; not listed for Gemma 4 | https://docs.aws.amazon.com/bedrock/latest/userguide/evaluation-support.html |
| Design Phase v1.1; Deployment Phase v1.0; previous Requirements and Budget documents | Architecture, decisions, sequence, proposals finalized here, requirement identifiers | Internal |